2025-2029 CDBG/Consolidated Plan And 2025 Annual Plan Application Process, Citizen Participation Plan
And Analysis of Impediments to Fair Housing Updates
Saturday, January 18, 2025
                                   Begin Notice for Proposed Projects

Monday January 27, 2025                                       Focus Group Meetings-Public/Sect 8 Housing, Homelessness, Housing; 2:30 p.m.
Tuesday, January 28, 2025                                      Focus Group Meetings-Economic Development, Non-Housing CD, Special Populations
                                                                                   10 a.m.
January 22 (Wed) & Jan 23 (Thurs), 2025
Non-Profit Technical Assistance Meetings-(1/22) 2 p.m. (1/23) at 10 a.m. & 2 p.m.
Tuesday, February 18, 2025
1st Public Hearing – 6:15 p.m.          Needs Assessment/Market Analysis                      

                                                                                  Opportunity to express needs                                                                 

                                                                                  Proposals/project requests
                                                                                  Receive comments on Draft Citizen               

                                                                                  Participation Plan, begin comment           
Tuesday, February 25, 2025
Deadline for Project Requests; Eval -March 27
February 25 - March 27, 2025
Internal review of projects and development of draft Consolidated Plan/Action Plan

Tuesday, March 18, 2025                                        2nd Public Hearing at 6:15-Receive comments on Analysis of Impediments, begin comment period on AI. End Comment Period on CPP

Tuesday, May 6, 2025
Announce CDBG funding recommendations
Tuesday, May 6, 2025
3rd Public Hearing at 6:15 p.m. – Receive comments on DRAFT Consolidated and Annual Action Plans 6:15 p.m. City Hall 

Friday, June 6, 2025
End Comment Period of 2025-2029 Consolidated and 2025 Annual Action Plans
Tuesday, June 17, 2025
Adoption of Final Plans by M&CC for Submission of 2025-2029 Five -Year Plan,  2025 Annual Action Plan, and Updated Citizen Participation Plan and Analysis of Impediments to Fair Housing to HUD for Review

September  2025
Final Approval by HUD

September
Distribution of Formal Funding Award Letters

October
Availability of Funds

*see special announcements on official City of Cumberland social media and website for any changes to the timeline or meetings

TIMELINE








